## Sheet1
Name | Date
Order parts | 2022-02-28
Start embedding linux | 2022-03-04
Finish embedding linux | 2022-04-22
Collected (Open, close, low, high, volume) Data | 2022-02-28
Collected EPS and insider data | 2022-03-28
Collect Inflation & Google Trends data | 2022-04-11
KEY
Not Statered | [13 empty] | Not Statered
Complete | [13 empty] | Complete
In Progress | [13 empty] | In Progress
Delayed | [13 empty] | Delayed
Cancelled | [13 empty] | Cancelled
Task has been undecided | 403 Timeline | [12 empty] | Task has been undecided | 404 Timeline
TASKS | Project Begin | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | TASKS | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28
Create GitHub for project - S | bar: 2022-08-29
Download Keras GRU library and generate a small test network | [13 empty] | Meet with sponsor - Gr | bar: 2022-08-29
Have all parts ordered and shipped | [13 empty] | Make GRU save best model for use - K | bar: 2022-08-29 to 2022-09-19
Collect primary market data (Open, close, low, high, volume) | [13 empty] | Test performance, accuracy, and FPGA compatibility - S & K | bar: 2022-08-29
Generate multidimensional arrays of different data combinations | [13 empty] | Market sentiment issue sorted out - X | bar: 2022-08-29 to 2022-09-26
Fully install and test the embedded Linux | [13 empty] | Debug Google Trends - X | bar: 2022-08-29 to 2022-09-05
Start Designing case and install cooling system | [13 empty] | Bi-weekly Update #1 - Gr | bar: 2022-09-05
Collect EPS data | [13 empty] | Create User input system - X & K | bar: 2022-09-12 to 2022-09-26
Test different layer numbers and neuron numbers | [13 empty] | Integrate GRU Script and Data Scrapping Script - X & K | bar: 2022-09-26 to 2022-10-10
Collect Insider Trading Data | [13 empty] | Bi-weekly Update #2 - Gr | bar: 2022-09-19
Collect Inflation rates | [13 empty] | Install Drivers for FPGA to run on monitor -S | bar: 2022-10-24
Implement an accuracy metric | [13 empty] | Start Designing case -S | bar: 2022-10-31
Market sentiment is assessed effectively | [10 empty] | 404 | 404 |  | Integrate the full software of GRU and Data Scrapper -Gr | bar: 2022-10-10 to 2022-10-31
Test performance, accuracy, and FPGA compatibility | [10 empty] | 404 | 404 |  | print case and mount onto FPGA - S | bar: 2022-11-07 to 2022-11-14
Design user input system | [12 empty] | 404 | Bi-weekly Update #3 - Gr | bar: 2022-10-03
Collect Google Trends data | [13 empty] | Bi-weekly Update #4 - Gr | bar: 2022-10-17
Finalize the data characteristics array | [13 empty] | Bi-weekly Update #5 - Gr | bar: 2022-10-31
Fully design and print case and mount onto FPGA | [13 empty] | Final Design Presentation - Gr | bar: 2022-11-07 to 2022-11-14
Final Presentation 403 | [13 empty] | Thanksgiving Break | bar: 2022-11-21
Final Report 403 | [13 empty] | FINAL REPORT DUE 3rd | bar: 2022-11-28
|  |  |  | GRU Arch. Execution | 2022-01-24 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25
Download Keras GRU library and generate a small test network | bar: 2022-02-07 to 2022-02-21
|  |  |  | Generate multidimensional arrays of different data combinations | [13 empty] | Not Started | bar: 2022-02-28 to 2022-03-07
|  |  |  | Test different layer numbers and neuron numbers | [13 empty] | Completed | bar: 2022-03-07 to 2022-03-28
|  |  |  | Implement an accuracy metric | [13 empty] | In Progress | bar: 2022-04-04 to 2022-04-18
|  |  |  | Finalize the data characteristics array | [13 empty] | Delayed | bar: 2022-04-04
|  |  |  | Create system to vary arrays to find best characteristics | [13 empty] | Canceled | bar: 2022-04-04 to 2022-04-25
Test performance and FPGA compatibility | bar: 2022-04-11 to 2022-04-18
[5 empty] | 2022-01-24 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25
Collect primary market data (Open, close, low, high, volume) | bar: 2022-02-28
Collect EPS data | bar: 2022-03-21 to 2022-03-28
Collect Inflation rates | bar: 2022-03-28 to 2022-04-04
Collect Insider Trading data | bar: 2022-04-04
Collect Google Trends data | bar: 2022-04-11
Market sentiment is assessed effectively | bar: 2022-04-11 to 2022-04-18